## Sheet1
3.5 GenAI-Powered Unified Authentication and Authorization (A&A) System for Multi-Cloud Environments
Team Members
1 . Naga Bala Subrahmanyam Gollapalli
2 . Rahul Patidar
Assignments/Task | Completed / not Completed | Done by person | ETA
|  |  | Date | Time
java jdk setup | completed | BOTH | 2024-10-09 | 4 hours
installation of keycloak | completed | BOTH
keycloak environment | completed | BOTH | 2024-10-09 | 4 hours
user creation | completed | BOTH
client creation | completed | BOTH
keycloak token generation & verification with postman | completed | BOTH | 2024-11-09 | 8-9 hours
verification with token (setup token in postman) | completed | Rahul | 2024-12-09 | 3 hours
verification with introspect(setup introspect in postman) | completed | Rahul | 2024-12-09 | 3 hours
verification with logout (setup logout with postman) | completed | Rahul | 2024-12-09 | 3 hours
login POST API creation | completed | Naga Bala | 2024-12-09 | 3 hours
user info GET API creation | completed | Naga Bala | 2024-12-09 | 3 hours
refresh_token POST API creation | completed | Naga Bala | 2024-12-09 | 3 hours
RBAC roles POST API creation | Inprogress | Naga Bala | 13/09/2024
RBAC roles GET API creation | Inprogress | Naga Bala | 13/09/2024
RBAC assign-role POST API creation | Inprogress | Naga Bala | 13/09/2024
login page creation | Inprogress | Naga Bala | 13/09/2024
keycloak integration with google idp | completed | Rahul | 13/09/2024 | 2 hours
keycloak integration with microsoft idp |  | Rahul
keycloak integration with github idp |  | Rahul
keycloak integration with login page | Inprogress | Rahul | 13/09/2024
docker implementation